## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 30
PROJECT NAME | Pulse Point Health App
PROJECT MENTOR (sponsor) | Vedika Parwal (Client)
TEAM MEMBERS | J Susheel Krishna
Krishna Koushik Mandava
Swaroop C
Pratyush Jena
Deekshitha Sagiraju

## Status
PROJECT NUMBER | 30
PROJECT NAME | Pulse Point Health App
PROJECT MENTOR (sponsor) | Vedika Parwal (Client)
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21)
Fix meeting with client | Coordination | Shambhavi(T.A) | 0.5 | 0.3 | Done |  | 0.2 | 66.6667
GIT Repository setup | Preparation | Deekshitha | 1 | 0.8 | Done |  | 0.2 | 25
Client meeting | Coordination | Pratyush,Susheel | 2 | 1.5 | Done | Make sure scoping questions are included | 0.5 | 33.3333
Questions for requirements | Preparation | Susheel,Swaroop | 1.5 | 2 | Done |  | -0.5 | 25
Research existing technology | Preparation | All | 3 | 3 | Done |  | 0 | 0
Project synopsis writeup | Documentation | Swaroop,Koushik | 1.5 | 2 | Done |  | -0.5 | 25
Identify role owners | Preparation | Swaroop,Koushik | 1 | 0.6 | Done | Multiple roles are OK - think about role & reponsibility distribution | 0.4 | 66.6667
Team Meeting | Coordination | Pratyush,Susheel | 1 | 1.5 | Done |  | -0.5 | 33.3333
Status tracker | Documentation | Deekshitha | 1 | 1.5 | Done |  | -0.5 | 33.3333
Week 2 (January 22 - January 28)
Project synopsis writeup | Documentation | Susheel,Koushik | 1.5 | 1 | Done |  | 0.5 | 50
MoM for client meet | Documentation | Deekshitha | 1 | 0.5 | Done |  | 0.5 | 100
Team Meeting | Coordination | Deekshitha,Pratyush | 1.5 | 1 | Done |  | 0.5 | 50
Fix meeting with client | Coordination | Swaroop,Susheel | 1 | 1 | Done |  | 0 | 0
data extraction research(iOS) | Preparation | Susheel,Koushik,Deekshitha | 3 | 3.5 | Done |  | -0.5 | 14.2857
data extraction research(Android) | Preparation | Swaroop,Pratyush | 3 | 3.5 | Done |  | -0.5 | 14.2857
Status tracker | Documentation | Koushik | 1 | 1 | Done |  | 0 | 0
Week 3 (January 29 - February 4)
Team Meeting | Coordination | Swaroop,Susheel | 1.5 | 1 | Done |  | 0.5 | 50
MoM for client meet | Documentation | Koushik | 1 | 0.5 | Done |  | 0.5 | 100
data extraction (Android) | Preparation | Susheel,Swaroop,pratyush | 2.5 | 2 | Done
Co-ordiantion with client (IOS) | Preparation | Koushik,Deekshitha | 2 | 1.5 | Done
Research on use of ml | Preparation | Koushik,Deekshitha | 0.5 | 0.5 | Done
Questions for requirements | Preparation | Pratyush,Susheel,swaroop | 1.5 | 1.2 | Done | Make sure scoping questions are included
Status tracker | Documentation | Deekshitha | 1 | 1 | Done |  | 0 | 0
Week 4
Co-ordiantion with client (IOS) | Preparation | Koushik,Deekshitha | 2.5 | 2 | Done |  | 0.5 | 25
data extraction (Android) | Preparation | Susheel,Swaroop,pratyush | 3 | 3 | Done
Research on use of ml | Preparation | Koushik,Deekshitha | 1 | 0.5 | Done
Team Meeting | Coordination | Deekshitha,Pratyush | 1 | 1.5 | Done
Technology requirements for SRS | Preparation | Swaroop,Susheel | 0.5 | 0.5 | Done
Status tracker | Documentation | Koushik | 0.5 | 0.5 | Done |  | 0 | 0
Week 5
data extraction (Android) | Preparation | Susheel,Swaroop,pratyush | 2.5 | 3 | Done
Research on use of ml | Preparation | Swaroop,Pratyush | 1 | 1 | Done
Team Meeting | Coordination | Deekshitha,Pratyush | 0.5 | 1 | Done |  | -0.5 | 50
Modifications in Project Plan | Documentation | Koushik,Susheel | 0.5 | 0.5 | Done
SRS document(Version 1) | Documentation | Koushik,Deekshitha,Susheel | 2.5 | 3.5 | Done
Status tracker | Documentation | Koushik | 0.5 | 0,.5 | Done |  | #VALUE! | #VALUE!
Week 6
Coordination with client(IOS) | Preparation | Koushik,Deekshitha | 3 | 3 | Done |  | 0 | 0
Research on health connect | Preparation | Susheel,Koushik | 4 | 3.5 | Done |  | 0.5 | 14.2857
Team Meeting | Coordination | Swaroop,Koushik | 1 | 0.5 | Done |  | 0.5 | 100
ML Techniques for data processing | Preparation | All | 8 |  | Done
Report Card generation(design) | Design | Swaroop,Pratyush | 10 |  | Ongoing
Technologies suitable for Android | Preparation | Susheel,Koushik,Deekshitha | 4 |  | Done
Test plan tracker | Preparation | Swaroop,Pratyush | 3 | 2.5 | Done
Status tracker | Documentation | Deekshitha | 0.5 | 0.5 | Done |  | 0 | 0
Week 7
Client meeting | Coordination | Swaroop, Deekshitha | 0.5 | 0.75 | Done |  | -0.25 | 33.3333
ML Techniques for data processing | Preparation | Swaroop, Pratyush | 1 | 1.5 | Done |  | -0.5 | 33.3333
Collecting raw data from watch sensor | Development | Koushik, Susheel | 3 |  | Done
Research on data from Aarogyasetu | Preparation | Deekshitha, Susheel | 0.5 | 0.5 | Done |  | 0 | 0
Team Meeting | Coordination | Pratyush, Deekshitha | 1 | 1 | Done |  | 0 | 0
MoM for client meet | Documentation | Susheel,Pratyush | 1 | 1 | Done
Design document | Documentation | Koushik,Deekshitha,Susheel | 2 |  | Done
Status tracker | Documentation | Koushik | 0.5 | 0.5 | Done |  | 0 | 0
Week 8
Team Meeting | Coordination | Swaroop,Pratyush | 0.5 | 0.5 | Done |  | 0 | 0
UI/UX for app | Development | Deekshitha,Koushik | 6 | 7 | Ongoing |  | -1 | 14.2857
Firebase setup | Development | Susheel | 2 | 2.5 | Done |  | -0.5 | 20
User authentication | Development | Koushik,Deekshitha | 2 | 2 | Done |  | 0 | 0
ML model building | Preparation | Swaroop,Pratyush | 7 | 6 | Done |  | 1 | 16.6667
Extraction of Data | Development | Susheel | 3 | 4 | Ongoing |  | -1 | 25
Status tracker | Documentation | Deekshitha | 0.5 | 0.5 | Done |  | 0 | 0
Note on C5: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on G5: swami: Insert your own comments
Note on H5: SE: This field is updated automatically